## Project Tracker
Vezeza Software Solutions
|  | Percent Over/Under to Flag: | 25%
Company | Project | Category | Assigned To | Estimated Start | Estimated Finish | Estimated Work (in hours) | Estimated Duration (in days) | Actual Start | Actual Finish | Flag | Actual Work (in hours) | Flag2 | Actual Duration (in days) | Deadline | Deadline2 | Bench
| Tuition World | Mobile Application Development | M Mounika | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Mobile Application Development | M Surendra | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Mobile Application Development | M Srinivas | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Web Application Development | P.NARESH KUMAR | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Web Application Development | M.AKHILESH | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Web Application Development | M.RAMA KRISHNA | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Testing | G Narendra | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | DevOps | Hemanth K | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Tuition World | Power Bi | T Vinod Kumar | 2023-01-10 | 2023-01-18 | 48 | 6 | 2023-01-10 | 2023-01-20 | 0 | 48 | 0 | 6 | 2023-01-21
| Ridere | Mobile Application Development | M Anuhya | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Mobile Application Development | A Vamsi | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Mobile Application Development | P Narendar | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Mobile Application Development | G Anoof Vijay | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Web Application Development | G.NIKHIL SAI | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Web Application Development | B.POOJITHA | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Web Application Development | A.GIRIDHAR | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Web Application Development | JJ.MANIDEEP | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Web Application Development | B Lakpathi | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | Testing | G Narendra | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
| Ridere | DevOps | Shiva Sai CH | 2023-01-10 | 2023-01-26 | 112 | 14 | 2023-01-10 | 2023-01-26 | 0 | 112 | 0 | 14 | 2023-01-22
SETUP

## Setup
Setup
Category Name | Employee Name | Technology
Mobile Application Development | M Mounika | Kotlin,Android Studio,Firebase
Mobile Application Development | M Anuhya | Kotlin,Android Studio,Firebase
Mobile Application Development | M Srinivas | Kotlin,Android Studio,Firebase
Mobile Application Development | A Vamsi | Kotlin,Android Studio,Firebase
Mobile Application Development | P Narendar | Kotlin,Android Studio,Firebase
Mobile Application Development | M Surendra | Kotlin,Android Studio,Firebase
Mobile Application Development | G Anoof Vijay | Kotlin,Android Studio,Firebase
Web Application Development | G.NIKHIL SAI | HTML,CSS,JavaScript,React,Node JS
Web Application Development | P.NARESH KUMAR | HTML,CSS,JavaScript,React,Node JS
Web Application Development | B.POOJITHA | HTML,CSS,JavaScript,React,Node JS
Web Application Development | M.AKHILESH | HTML,CSS,JavaScript,React,Node JS
Web Application Development | A.GIRIDHAR | HTML,CSS,JavaScript,React,Node JS
Web Application Development | JJ.MANIDEEP | HTML,CSS,JavaScript,React,Node JS
Web Application Development | M.RAMA KRISHNA | HTML,CSS,JavaScript,React,Node JS
DevOps | Shiva Sai CH | AWS,Terraform,JIRA,Ansible,Cloudwatch,Kubernettes,Jenkins
DevOps | Hemanth K | AWS,Terraform,JIRA,Ansible,Cloudwatch,Kubernettes,Jenkins
Testing | G Narendra | Manual,Automation
Power Bi | T Vinod Kumar | Bi Tools
Web Application Development | B Lakpathi(TL) | HTML,CSS,JavaScript,React,Node JS
Web Application Development | SJ Purushothaman™ | HTML,CSS,JavaScript,React,Node JS
Mobile Application Development | Purushottam™ | Kotlin,Android Studio,Firebase
Mobile Application Development | Bhavani(TL) | Kotlin,Android Studio,Firebase
PROJECTS